## Sheet1
Project Management Tracker - IT department
Project Resources
Project Staff | Amit Shah
| Developer | Task | Status | Response person | Start date | Duration | Holidays | End Date
Session 1 | Likhitha | Document for review | Not started | Manager- Abdul | 2023-05-25 | 6 | 2023-05-28 | 2023-06-02
| Oliviya | Dashboard creation | In progress | Team Lead- Rehana | 2023-05-12 | 10 | 2023-05-14 | 2023-05-26
| Navya | Bussiness analysis | Changes needed | Team Lead- Rehana | 2023-04-11 | 9 | 2023-04-14 | 2023-04-25
Session 2
Session 3
Formulas:
End Date = WORKDAY([Start date],[Duration],[Holidays])

## Developers
Navya
Likhitha
Oliviya
Aneesha
Asin

## Response Person
Manager- Abdul
Marketing head- Jameel
Product head- Rizwanaa
Supervisor- Rahamath
Team Lead- Rehana

## Status
Not started
In progress
Ready for review
Changes needed
Ready for final review
Completed